## ClickUp Import
Sprint List | Task ID | Task Name | Description | Assignee | Reviewer | Status | Priority | Start Date | Due Date | Workstream | Tags | Dependencies | Effort Hours | Deliverable Path | Acceptance Criteria | Milestone | Risk | Data Status
S1 — Foundation & Data Freeze | S1-VEN-01 | [S1-VEN-01] Clean pipeline rerun dan baseline QA | Jalankan pipeline dari snapshot raw pada environment bersih dan rekam seluruh pemeriksaan. | Venedict | Stephen | READY | Urgent | 2026-08-24 | 2026-08-30 | Data | tb-insight;real-data;s1;data |  | 12 | results/qa/s1_pipeline_qa.md | Pipeline selesai tanpa error; panel 912 baris, 38 provinsi, 24 bulan; duplicate key dan missing wajib = 0. |  | High | Provisional
S1 — Foundation & Data Freeze | S1-VEN-02 | [S1-VEN-02] Freeze dataset v1, checksum, dictionary, ledger | Bekukan input/output utama serta metadata provenance untuk analysis baseline. | Venedict | Adzki | READY | Urgent | 2026-08-24 | 2026-08-30 | Data | tb-insight;real-data;s1;data | S1-VEN-01 | 10 | data/processed/release_v1/ | Manifest berisi checksum, tanggal akses, unit, periode, sumber, dan limitation; raw tidak berubah. |  | High | Frozen
S1 — Foundation & Data Freeze | S1-STE-01 | [S1-STE-01] Preregister analysis plan internal | Tetapkan estimand, outcome, offset, fixed effects, lag 0–3, interaksi, dan sensitivity inti. | Stephen | Venedict | READY | Urgent | 2026-08-24 | 2026-08-30 | Modeling | tb-insight;real-data;s1;modeling | S1-VEN-01 | 14 | docs/analysis-plan-v1.md | Satu model primer dan daftar sensitivity tertulis sebelum model lanjutan dijalankan; tidak ada forecasting operasional. |  | High | Provisional
S1 — Foundation & Data Freeze | S1-STE-02 | [S1-STE-02] Audit hasil PPML preliminary | Verifikasi formula, offset, FE, standard error, label variabel, dan interpretasi hasil awal. | Stephen | Venedict | READY | High | 2026-08-24 | 2026-08-30 | Modeling | tb-insight;real-data;s1;modeling | S1-STE-01 | 8 | results/model_audit_s1.md | Setiap coefficient dapat ditelusuri ke script dan diberi interpretasi IRR yang benar; issue log tersedia. |  | Medium | Not Applicable
S1 — Foundation & Data Freeze | S1-DAM-01 | [S1-DAM-01] Audit boundary, CRS, dan province IDs | Cocokkan 38 provinsi pada panel dengan geometri, kode wilayah, centroid, dan perubahan Papua. | Dame | Venedict | READY | Urgent | 2026-08-24 | 2026-08-30 | Spatial | tb-insight;real-data;s1;spatial | S1-VEN-02 | 12 | results/spatial/boundary_audit.csv | Semua 38 provinsi match satu-ke-satu; CRS dan geometri valid; mismatch = 0. |  | High | Frozen
S1 — Foundation & Data Freeze | S1-DAM-02 | [S1-DAM-02] Spatial weights decision memo | Definisikan queen/rook/KNN kandidat dan aturan eksplisit untuk provinsi kepulauan. | Dame | Stephen | READY | High | 2026-08-24 | 2026-08-30 | Spatial | tb-insight;real-data;s1;spatial | S1-DAM-01 | 8 | docs/spatial-weights-decision.md | Metode primer dan alternatif ditetapkan; islands/Papua tidak memiliki neighbor secara tidak sengaja. |  | Medium | Not Applicable
S1 — Foundation & Data Freeze | S1-ERI-01 | [S1-ERI-01] Information architecture dan user flow | Susun perjalanan pengguna Overview–Trend–Map–Methods–Sources sesuai pertanyaan penelitian. | Erin | Dame | READY | High | 2026-08-24 | 2026-08-30 | Product | tb-insight;real-data;s1;product |  | 12 | docs/design/ia-user-flow.pdf | Lima halaman inti, tujuan pengguna, dan alur navigasi disetujui pada review lintas peran. |  | Medium | Not Applicable
S1 — Foundation & Data Freeze | S1-ERI-02 | [S1-ERI-02] Provenance dan provisional display rules | Rancang pola UI untuk definisi outcome, status data 2025, sumber, ketidakpastian, dan limitation. | Erin | Adzki | READY | Urgent | 2026-08-24 | 2026-08-30 | Product | tb-insight;real-data;s1;product | S1-ERI-01,S1-VEN-02 | 10 | docs/design/data-status-patterns.pdf | Warning 2025 dan definisi treatment_started terlihat pada konteks angka; tidak hanya di footer. |  | Medium | Not Applicable
S1 — Foundation & Data Freeze | S1-ADZ-01 | [S1-ADZ-01] Literature evidence matrix | Kurasi literatur TB–iklim–sosial–spatial dan petakan temuan, metode, gap, serta relevansi. | Adzki | Stephen | READY | Urgent | 2026-08-24 | 2026-08-30 | Writing | tb-insight;real-data;s1;writing |  | 18 | docs/writing/literature-evidence-matrix.xlsx | Setiap klaim memiliki DOI/URL, desain, lokasi, outcome, exposure, metode, limitation, dan relevansi. |  | Medium | Not Applicable
S1 — Foundation & Data Freeze | S1-ADZ-02 | [S1-ADZ-02] Manuscript outline dan terminology glossary | Buat outline section-level serta glossary istilah wajib/terlarang. | Adzki | Venedict | READY | High | 2026-08-24 | 2026-08-30 | Writing | tb-insight;real-data;s1;writing | S1-ADZ-01,S1-STE-01 | 10 | docs/writing/manuscript-outline-v1.md | Outline menjawab empat research questions; treatment initiation tidak disebut insidensi; limitation teralokasi. |  | Medium | Not Applicable
S1 — Foundation & Data Freeze | M1 | [M1] M1 — Data & Question Freeze | Gate review atas dataset, research question, model primer, spatial contract, UX contract, dan outline. | Venedict | Seluruh Tim | READY | Urgent | 2026-08-24 | 2026-08-30 | QA | tb-insight;real-data;s1;qa | S1-VEN-02,S1-STE-01,S1-DAM-02,S1-ERI-02,S1-ADZ-02 | 5 | docs/decisions/M1-signoff.md | Lima workstream sign-off; open issue High memiliki owner dan due date. | M1 Data & Question Freeze | High | Frozen
S2 — EDA & Spatial Foundation | S2-VEN-01 | [S2-VEN-01] National temporal EDA | Analisis tren bulanan nasional: count, rate per population, distribusi, outlier, dan pola kalender. | Venedict | Stephen | BACKLOG | Urgent | 2026-08-31 | 2026-09-06 | Data | tb-insight;real-data;s2;data | M1 | 14 | results/eda/national_temporal/ | Semua figure diturunkan dari panel frozen; count dan rate tidak tertukar; 2025 ditandai provisional. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-VEN-02 | [S2-VEN-02] Province profiles dan data maturity | Buat profil 38 provinsi dan audit data maturity/outcome_pending. | Venedict | Adzki | BACKLOG | High | 2026-08-31 | 2026-09-06 | Data | tb-insight;real-data;s2;data | M1 | 16 | results/eda/province_profiles/ | 38 profil tersedia dengan unit/period/source; anomalous observations memiliki flag dan catatan. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-STE-01 | [S2-STE-01] Baseline PPML fixed effects | Jalankan model primer tanpa exposure lanjutan dan simpan coefficient, CI, diagnostics, serta metadata. | Stephen | Venedict | BACKLOG | Urgent | 2026-08-31 | 2026-09-06 | Modeling | tb-insight;real-data;s2;modeling | M1 | 18 | results/models/baseline_ppml/ | Offset populasi dan FE sesuai plan; convergence terdokumentasi; output machine-readable tersedia. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-STE-02 | [S2-STE-02] Baseline diagnostics dan model table v0 | Periksa dispersion, influential provinces, convergence, residuals, serta bangun tabel model awal. | Stephen | Venedict | BACKLOG | High | 2026-08-31 | 2026-09-06 | Modeling | tb-insight;real-data;s2;modeling | S2-STE-01 | 10 | results/models/baseline_diagnostics/ | Diagnostic checklist lengkap dan tidak ada model gagal yang dilaporkan sebagai final. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-DAM-01 | [S2-DAM-01] Versioned spatial weights dan Global Moran | Bangun weights primer/alternatif dan hitung Global Moran's I untuk count/rate atau residual sesuai protokol. | Dame | Stephen | BACKLOG | Urgent | 2026-08-31 | 2026-09-06 | Spatial | tb-insight;real-data;s2;spatial | M1 | 18 | results/spatial/weights_v1/ | Weights, neighbor list, seed/permutations, dan Moran output dapat direproduksi. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-DAM-02 | [S2-DAM-02] Initial LISA dan sensitivity neighbors | Jalankan LISA awal dan bandingkan klasifikasi pada weights alternatif. | Dame | Stephen | BACKLOG | High | 2026-08-31 | 2026-09-06 | Spatial | tb-insight;real-data;s2;spatial | S2-DAM-01 | 13 | results/spatial/lisa_v0/ | Cluster label, p-value/permutation, multiple testing note, dan stability comparison tersedia. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-ERI-01 | [S2-ERI-01] High-fidelity research dashboard wireframes | Rancang Overview, Trends, Hotspots, Province Detail, Methods, dan Sources. | Erin | Dame | BACKLOG | Urgent | 2026-08-31 | 2026-09-06 | Product | tb-insight;real-data;s2;product | M1,S2-VEN-01 | 20 | docs/design/wireframes-v1.pdf | Semua state utama, responsive breakpoint, source note, provisional warning, dan empty state terlihat. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-ERI-02 | [S2-ERI-02] API–UI data contract | Definisikan endpoint, schema, unit, filter, error, freshness, dan provenance yang dibutuhkan UI. | Erin | Venedict | BACKLOG | High | 2026-08-31 | 2026-09-06 | Product | tb-insight;real-data;s2;product | S2-ERI-01 | 10 | docs/design/api-ui-contract.md | Tidak ada angka hardcoded; setiap widget memetakan field, unit, source, dan fallback. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-ADZ-01 | [S2-ADZ-01] Draft Data and Methods v0.5 | Tulis sumber, unit analisis, outcome, exposure, covariates, spatial method, model, dan ethics/data limits. | Adzki | Venedict | BACKLOG | Urgent | 2026-08-31 | 2026-09-06 | Writing | tb-insight;real-data;s2;writing | M1,S1-ADZ-01 | 16 | docs/writing/manuscript-methods-v0.5.md | Setiap definisi cocok dengan codebook/analysis plan dan memiliki sitasi sumber. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | S2-ADZ-02 | [S2-ADZ-02] Descriptive narrative dan table shells | Siapkan Table 1/Figure callouts dan narasi faktual tanpa overclaim. | Adzki | Venedict | BACKLOG | High | 2026-08-31 | 2026-09-06 | Writing | tb-insight;real-data;s2;writing | S2-VEN-01,S2-VEN-02 | 10 | docs/writing/descriptive-results-v0.3.md | Semua placeholder memakai output ID; footnote provisional dan unit lengkap. |  | Medium | Not Applicable
S2 — EDA & Spatial Foundation | M2 | [M2] M2 — Descriptive & Spatial Foundation | Review EDA, baseline PPML, spatial foundation, wireframes, dan Methods. | Dame | Seluruh Tim | BACKLOG | Urgent | 2026-08-31 | 2026-09-06 | QA | tb-insight;real-data;s2;qa | S2-VEN-01,S2-VEN-02,S2-STE-02,S2-DAM-02,S2-ERI-02,S2-ADZ-02 | 4 | docs/decisions/M2-signoff.md | Angka, peta, narasi, dan widget merujuk output pipeline yang sama. | M2 Descriptive & Spatial Foundation | High | Frozen
S3 — Climate, Social & Prototype | S3-VEN-01 | [S3-VEN-01] Climate anomalies, seasonality, dan lag features | Bangun anomaly/z-score serta lag 0–3 untuk temperatur, kelembapan, dan hujan. | Venedict | Stephen | BACKLOG | Urgent | 2026-09-07 | 2026-09-13 | Data | tb-insight;real-data;s3;data | M2 | 18 | data/processed/features/climate_lags_v1.csv | Tidak ada leakage; definisi baseline 1991–2020 tercatat; boundary month handling eksplisit. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-VEN-02 | [S3-VEN-02] Feature matrix QA | Audit completeness, range, correlations, lag alignment, dan social covariate reference periods. | Venedict | Dame | BACKLOG | High | 2026-09-07 | 2026-09-13 | Data | tb-insight;real-data;s3;data | S3-VEN-01 | 10 | results/qa/feature_matrix_qa.md | QA lulus atau setiap exception terdokumentasi; annual BPS tidak dilabeli bulanan. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-STE-01 | [S3-STE-01] PPML climate lag models | Estimasi exposure dan lag sesuai analysis plan, satu family pada satu waktu. | Stephen | Venedict | BACKLOG | Urgent | 2026-09-07 | 2026-09-13 | Modeling | tb-insight;real-data;s3;modeling | S3-VEN-02 | 16 | results/models/climate_lags/ | Seluruh model pre-specified dijalankan; coefficient/CI/convergence tersedia; selection rule terdokumentasi. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-STE-02 | [S3-STE-02] Social vulnerability interactions | Uji interaksi iklim dengan kemiskinan, kepadatan, dan sanitasi satu per satu. | Stephen | Adzki | BACKLOG | High | 2026-09-07 | 2026-09-13 | Modeling | tb-insight;real-data;s3;modeling | S3-STE-01 | 14 | results/models/social_interactions/ | Tidak ada kitchen-sink model; multiplicity dan uncertainty dibahas; marginal contrast tersedia. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-DAM-01 | [S3-DAM-01] Hotspot persistence analysis | Identifikasi hotspot/coldspot persisten antarbulan dan stabilitas klasifikasi. | Dame | Stephen | BACKLOG | Urgent | 2026-09-07 | 2026-09-13 | Spatial | tb-insight;real-data;s3;spatial | M2 | 18 | results/spatial/hotspot_persistence/ | Definisi persistence pre-specified; peta tidak menyembunyikan non-significant/insufficient observations. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-DAM-02 | [S3-DAM-02] Climate and vulnerability map exploration | Eksplorasi peta small multiples yang menghubungkan anomali iklim, treatment initiation, dan kerentanan. | Dame | Erin | BACKLOG | High | 2026-09-07 | 2026-09-13 | Spatial | tb-insight;real-data;s3;spatial | S3-VEN-02,S3-DAM-01 | 12 | results/spatial/exploratory_maps/ | Skala/legend konsisten dan tidak mengimplikasikan kausalitas; kandidat peta utama ditandai. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-ERI-01 | [S3-ERI-01] Frontend alpha — trends and maps | Implementasikan komponen tren, peta, filter provinsi/periode, tooltip, legend, dan loading state. | Erin | Dame | BACKLOG | Urgent | 2026-09-07 | 2026-09-13 | Product | tb-insight;real-data;s3;product | S2-ERI-02,S3-DAM-01 | 22 | frontend/ | Alpha membaca API/mock contract yang sama; tidak memakai dataset synthetic; state utama berfungsi. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-ERI-02 | [S3-ERI-02] Methods, provenance, dan limitation pages | Implementasikan halaman sumber/metode serta context note pada visual utama. | Erin | Adzki | BACKLOG | High | 2026-09-07 | 2026-09-13 | Product | tb-insight;real-data;s3;product | S2-ERI-02,S2-ADZ-01 | 12 | frontend/ | Source, date accessed, unit, outcome definition, provisional warning, dan limitation dapat ditemukan pengguna. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-ADZ-01 | [S3-ADZ-01] Methods climate and spatial revision | Perbarui Methods berdasarkan feature engineering dan spatial analysis aktual. | Adzki | Dame | BACKLOG | High | 2026-09-07 | 2026-09-13 | Writing | tb-insight;real-data;s3;writing | S3-VEN-02,S3-DAM-01 | 12 | docs/writing/manuscript-methods-v0.8.md | Parameter lag, baseline iklim, weights, permutations, dan multiple testing ditulis tepat. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | S3-ADZ-02 | [S3-ADZ-02] Results shell dan novelty claim audit | Bangun Results shell serta audit apakah novelty claim benar-benar didukung evidence matrix. | Adzki | Stephen | BACKLOG | High | 2026-09-07 | 2026-09-13 | Writing | tb-insight;real-data;s3;writing | S3-STE-02,S3-ADZ-01 | 12 | docs/writing/results-shell-v0.5.md | Setiap klaim memiliki output ID dan referensi; novelty tidak dinyatakan absolut tanpa bukti. |  | Medium | Not Applicable
S3 — Climate, Social & Prototype | M3 | [M3] M3 — Analysis Alpha | Pilih kandidat model/peta berdasarkan protocol, robustness, dan interpretability. | Stephen | Seluruh Tim | BACKLOG | Urgent | 2026-09-07 | 2026-09-13 | QA | tb-insight;real-data;s3;qa | S3-STE-02,S3-DAM-02,S3-ERI-02,S3-ADZ-02 | 5 | docs/decisions/M3-signoff.md | Model kandidat tidak dipilih hanya berdasarkan p-value; open sensitivity ditetapkan. | M3 Analysis Alpha | High | Provisional
S4 — Sensitivity & Integration | S4-VEN-01 | [S4-VEN-01] Data maturity, disaster, outlier, denominator sensitivity | Jalankan sensitivity terkait provisional 2025, bencana, influential observations, dan denominator. | Venedict | Stephen | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Data | tb-insight;real-data;s4;data | M3 | 20 | results/sensitivity/data/ | Setiap sensitivity memiliki rationale, sample change, output, dan comparison terhadap primary. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-VEN-02 | [S4-VEN-02] Analysis output manifest | Buat manifest ID untuk seluruh tabel, figure, map, dataset, script, dan source version. | Venedict | Erin | BACKLOG | High | 2026-09-14 | 2026-09-20 | QA | tb-insight;real-data;s4;qa | S4-VEN-01 | 8 | results/output_manifest.csv | Setiap output yang tampil di dashboard/manuskrip memiliki path, version, timestamp, dan owner. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-STE-01 | [S4-STE-01] Model sensitivity dan uncertainty synthesis | Jalankan alternative specifications, exclusion checks, dan ringkas kestabilan estimate. | Stephen | Venedict | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Modeling | tb-insight;real-data;s4;modeling | S4-VEN-01 | 17 | results/sensitivity/models/ | Primary estimate dibandingkan secara konsisten; disagreement dilaporkan, bukan disembunyikan. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-STE-02 | [S4-STE-02] Residual spatial autocorrelation | Uji autokorelasi spasial residual model utama dan tentukan implikasinya. | Stephen | Dame | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Modeling | tb-insight;real-data;s4;modeling | S4-STE-01,S3-DAM-01 | 10 | results/spatial/residual_moran/ | Residual Moran dengan weights primer/alternatif tersedia dan limitation/model decision tercatat. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-DAM-01 | [S4-DAM-01] Island and Papua spatial sensitivity | Uji KNN/distance/contiguity serta pengaruh konfigurasi wilayah kepulauan/Papua. | Dame | Stephen | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Spatial | tb-insight;real-data;s4;spatial | S4-STE-02 | 18 | results/spatial/weights_sensitivity/ | Cluster yang tidak stabil ditandai; neighbor graph dan parameter tersedia. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-DAM-02 | [S4-DAM-02] Final spatial ID and geometry QA | Verifikasi join, geometry validity, projection, topology, legends, dan missing map records. | Dame | Venedict | BACKLOG | High | 2026-09-14 | 2026-09-20 | Spatial | tb-insight;real-data;s4;spatial | S4-DAM-01 | 8 | results/qa/spatial_final_qa.md | 38 provinsi tampil tepat; missing geometry/join = 0; QA checklist ditandatangani. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-ERI-01 | [S4-ERI-01] Backend–frontend real-data integration | Hubungkan semua halaman inti dengan endpoint real-data dan output manifest. | Erin | Venedict | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Product | tb-insight;real-data;s4;product | S4-VEN-02,S4-DAM-02 | 22 | frontend/ | Tidak ada angka hardcoded; filters konsisten; provenance mengacu output manifest. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-ERI-02 | [S4-ERI-02] Accessibility, error, empty, dan download states | Tambahkan keyboard/focus, contrast, alt text hook, network errors, empty state, dan export metadata. | Erin | Adzki | BACKLOG | High | 2026-09-14 | 2026-09-20 | Product | tb-insight;real-data;s4;product | S4-ERI-01 | 12 | frontend/ | Critical flows dapat diakses keyboard; error tidak menampilkan angka stale; export menyertakan metadata. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-ADZ-01 | [S4-ADZ-01] Full manuscript draft v0.7 | Gabungkan Introduction, Methods, Results awal, Discussion, dan Limitations. | Adzki | Stephen | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Writing | tb-insight;real-data;s4;writing | S4-STE-01,S4-DAM-01 | 22 | docs/writing/manuscript-v0.7.docx | Semua section utama terisi; causal language dihapus; limitation dua tahun dan provisional jelas. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | S4-ADZ-02 | [S4-ADZ-02] Number and claim reconciliation | Cocokkan angka/narasi manuskrip dengan output manifest dan dashboard. | Adzki | Venedict | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | Writing | tb-insight;real-data;s4;writing | S4-VEN-02,S4-ADZ-01,S4-ERI-01 | 12 | docs/writing/claim-audit-s4.xlsx | Setiap angka memiliki output ID; mismatch terbuka = 0 untuk hasil utama. |  | Medium | Not Applicable
S4 — Sensitivity & Integration | M4 | [M4] M4 — Analysis Freeze | Bekukan angka, model, tabel, dan peta utama; perubahan setelah gate memakai change request. | Stephen | Seluruh Tim | BACKLOG | Urgent | 2026-09-14 | 2026-09-20 | QA | tb-insight;real-data;s4;qa | S4-VEN-02,S4-STE-02,S4-DAM-02,S4-ERI-02,S4-ADZ-02 | 5 | docs/decisions/M4-signoff.md | Primary/sensitivity complete; residual spatial diperiksa; angka utama konsisten lintas produk. | M4 Analysis Freeze | High | Frozen
S5 — Release Candidate | S5-VEN-01 | [S5-VEN-01] Release pipeline, codebook, dan QA report | Finalisasi pipeline reproducible, codebook, source ledger, checksums, dan QA report. | Venedict | Stephen | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | Data | tb-insight;real-data;s5;data | M4 | 20 | data/processed/release_candidate/ | Satu command menghasilkan seluruh output release; validator PASS; provenance lengkap. |  | Medium | Not Applicable
S5 — Release Candidate | S5-VEN-02 | [S5-VEN-02] Publication analytical tables | Hasilkan tabel deskriptif/model/sensitivity siap publikasi dari manifest frozen. | Venedict | Adzki | BACKLOG | High | 2026-09-21 | 2026-09-27 | Data | tb-insight;real-data;s5;data | S5-VEN-01 | 12 | results/publication/tables/ | Tabel memiliki title, unit, N, footnote, source, provisional note, dan machine-readable copy. |  | Medium | Not Applicable
S5 — Release Candidate | S5-STE-01 | [S5-STE-01] Final model report dan interpretation | Finalisasi primary/secondary result, CI, diagnostics, dan interpretasi plain language. | Stephen | Adzki | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | Modeling | tb-insight;real-data;s5;modeling | M4,S5-VEN-02 | 20 | results/publication/model_report.md | Interpretasi konsisten dengan scale/link; non-significant dan unstable findings tidak dihilangkan. |  | Medium | Not Applicable
S5 — Release Candidate | S5-STE-02 | [S5-STE-02] Robustness appendix | Susun seluruh sensitivity dalam appendix ringkas dan audit trail keputusan. | Stephen | Venedict | BACKLOG | High | 2026-09-21 | 2026-09-27 | Modeling | tb-insight;real-data;s5;modeling | S5-STE-01 | 12 | results/publication/robustness_appendix.xlsx | Setiap row berisi specification, rationale, estimate, CI, N, convergence, dan conclusion. |  | Medium | Not Applicable
S5 — Release Candidate | S5-DAM-01 | [S5-DAM-01] Publication-quality maps | Finalisasi peta utama/supplement dengan layout, legend, projection, uncertainty, dan provenance. | Dame | Erin | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | Spatial | tb-insight;real-data;s5;spatial | M4 | 22 | results/publication/maps/ | Peta readable grayscale/color-safe; class breaks konsisten; source/period/unit tampil. |  | Medium | Not Applicable
S5 — Release Candidate | S5-DAM-02 | [S5-DAM-02] Cartography QA dan alt-text package | Lakukan peer QA dan tulis deskripsi aksesibel untuk setiap peta. | Dame | Adzki | BACKLOG | High | 2026-09-21 | 2026-09-27 | Spatial | tb-insight;real-data;s5;spatial | S5-DAM-01 | 8 | results/publication/maps/map_manifest.csv | Setiap map memiliki alt-text, output ID, source, unit, period, method, dan limitation. |  | Medium | Not Applicable
S5 — Release Candidate | S5-ERI-01 | [S5-ERI-01] Moderated usability test | Uji lima alur utama dengan skenario, catat severity, dan prioritaskan defect. | Erin | Dame | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | Product | tb-insight;real-data;s5;product | M4 | 12 | docs/design/usability-test-s5.md | Minimal 5 sesi atau expert reviews; issue memiliki evidence, severity P0–P2, owner, dan disposition. |  | Medium | Not Applicable
S5 — Release Candidate | S5-ERI-02 | [S5-ERI-02] Dashboard release candidate | Tutup issue prioritas, polish responsive hierarchy, dan buat RC deployment package. | Erin | Venedict | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | Product | tb-insight;real-data;s5;product | S5-ERI-01,S5-DAM-02 | 18 | frontend/ | Tidak ada defect P0; P1 memiliki resolution; build/test script dan demo flow terdokumentasi. |  | Medium | Not Applicable
S5 — Release Candidate | S5-ADZ-01 | [S5-ADZ-01] Manuscript v1 and supplementary materials | Selesaikan full manuscript, abstract, discussion, limitation, tables/figures, dan supplement. | Adzki | Stephen | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | Writing | tb-insight;real-data;s5;writing | S5-STE-02,S5-DAM-02 | 22 | docs/writing/manuscript-v1.docx | Tidak ada placeholder hasil utama; callout tabel/gambar benar; claim sesuai evidence. |  | Medium | Not Applicable
S5 — Release Candidate | S5-ADZ-02 | [S5-ADZ-02] Reference and reproducibility appendix audit | Audit referensi, DOI, dataset citation, source ledger, software version, dan reproducibility steps. | Adzki | Venedict | BACKLOG | High | 2026-09-21 | 2026-09-27 | Writing | tb-insight;real-data;s5;writing | S5-ADZ-01,S5-VEN-01 | 10 | docs/writing/reproducibility-appendix.md | Broken DOI/URL = 0; seluruh data/software citation dan access date tersedia. |  | Medium | Not Applicable
S5 — Release Candidate | M5 | [M5] M5 — Release Candidate Review | Demo internal, scientific review, manuscript review, dan defect triage. | Erin | Seluruh Tim | BACKLOG | Urgent | 2026-09-21 | 2026-09-27 | QA | tb-insight;real-data;s5;qa | S5-VEN-01,S5-STE-02,S5-DAM-02,S5-ERI-02,S5-ADZ-02 | 4 | docs/decisions/M5-signoff.md | RC dapat didemonstrasikan; defect P0 = 0; P1 memiliki owner sebelum S6. | M5 Release Candidate | High | Frozen
S6 — Final Validation & Handover | S6-VEN-01 | [S6-VEN-01] Clean-environment independent reproduction | Rebuild data dan output utama dari README pada environment bersih dan catat durasi/error. | Venedict | Stephen | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | QA | tb-insight;real-data;s6;qa | M5 | 18 | results/reproduction/clean_run_log.md | Pipeline PASS; checksums output utama cocok atau perbedaan dijelaskan; langkah manual = 0/minimal. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-VEN-02 | [S6-VEN-02] Final data and model release manifest | Kunci version, checksums, licensed-data exclusions, dan daftar artifact final. | Venedict | Adzki | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | Data | tb-insight;real-data;s6;data | S6-VEN-01 | 8 | deliverables/final_release_manifest.csv | Artifact final dapat ditelusuri; raw restricted tidak ikut package; synthetic artifact = 0. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-STE-01 | [S6-STE-01] Independent model rerun dan sign-off | Jalankan model utama dari release oleh reviewer dan cocokkan angka manuskrip. | Stephen | Venedict | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | Modeling | tb-insight;real-data;s6;modeling | S6-VEN-01 | 16 | results/reproduction/model_signoff.md | Coefficient/CI/N utama cocok dengan manuscript/table; discrepancy terbuka = 0. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-STE-02 | [S6-STE-02] Plain-language findings and boundaries | Ringkas temuan, uncertainty, apa yang tidak dapat disimpulkan, dan next-data needs. | Stephen | Adzki | BACKLOG | High | 2026-09-28 | 2026-10-04 | Writing | tb-insight;real-data;s6;writing | S6-STE-01 | 8 | deliverables/key_findings_and_limits.md | Tidak ada causal/forecast claim; treatment initiation dan provisional status disebut eksplisit. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-DAM-01 | [S6-DAM-01] Final spatial QA dan asset handover | Final audit weights, maps, layers, joins, metadata, dan reproducibility spatial. | Dame | Erin | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | Spatial | tb-insight;real-data;s6;spatial | M5,S6-STE-01 | 16 | deliverables/spatial_handover/ | 38 provinsi benar; seluruh map/layer memiliki version, CRS, source, dan generation script. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-ERI-01 | [S6-ERI-01] End-to-end QA dan product handover | Tutup P0/P1, test critical flows/build, serta tulis runbook dan demo script. | Erin | Dame | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | Product | tb-insight;real-data;s6;product | M5,S6-DAM-01 | 20 | deliverables/product_handover/ | Critical flow PASS; P0/P1 = 0; runbook baru dapat diikuti reviewer non-pembuat. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-ADZ-01 | [S6-ADZ-01] Final manuscript and submission checklist | Final language, references, tables/figures, supplement, author checklist, dan cover summary. | Adzki | Stephen | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | Writing | tb-insight;real-data;s6;writing | S6-STE-02,S6-DAM-01,S6-ERI-01 | 20 | deliverables/manuscript_final/ | Angka final reconciled; references complete; limitation visible; checklist siap submission. |  | Medium | Not Applicable
S6 — Final Validation & Handover | S6-ALL-01 | [S6-ALL-01] Dry run presentation and adversarial review | Latihan demo serta Q&A kritis pada metode, data, spatial assumptions, novelty, dan limitation. | Adzki | Seluruh Tim | BACKLOG | High | 2026-09-28 | 2026-10-04 | QA | tb-insight;real-data;s6;qa | S6-VEN-02,S6-STE-02,S6-DAM-01,S6-ERI-01,S6-ADZ-01 | 7 | deliverables/final_dry_run_notes.md | Setiap pertanyaan kritis memiliki jawaban/evidence owner; blocking issue = 0. |  | Medium | Not Applicable
S6 — Final Validation & Handover | M6 | [M6] M6 — Final Research Package Sign-off | Go/no-go final atas data, model, maps, dashboard, manuscript, dan handover. | Adzki | Seluruh Tim | BACKLOG | Urgent | 2026-09-28 | 2026-10-04 | QA | tb-insight;real-data;s6;qa | S6-ALL-01 | 5 | deliverables/final_signoff.md | Lima anggota sign-off; validator PASS; P0/P1 = 0; final package lengkap. | M6 Final Research Package | High | Frozen

## Executive Brief
TB-INSIGHT — 6-Week Sprint Control Center
24 Aug 2026–4 Oct 2026 ¦ Real-data spatio-temporal research ¦ 38 provinces × 24 months
Owner | Role | Tasks | Hours | Primary accountability | Reviewer pair | WIP limit | Final sign-off
Venedict | Data Scientist — Data/QA Lead | 13 | 171 | Pipeline, freeze, EDA, feature engineering, reproduction | Stephen | 2 | Data & reproducibility
Stephen | Data Scientist — Modeling Lead | 14 | 173 | Analysis plan, PPML, interactions, sensitivity | Venedict | 2 | Model validity
Dame | Spatial Analyst — Spatial Lead | 12 | 157 | Boundaries, weights, Moran/LISA, maps | Erin / Stephen | 2 | Spatial validity
Erin | UI/UX Designer — Product Lead | 12 | 174 | IA, frontend, provenance UX, usability | Dame / Venedict | 2 | Product quality
Adzki | Scientific Writer — Evidence Lead | 13 | 176 | Literature, manuscript, claims, limitations | All technical leads | 2 | Scientific narrative
Sprint | Dates | Theme | Exit milestone | Task count | Hours | Primary risk | Gate owner
S1 | 24–30 Aug | Foundation & Data Freeze | M1 Data & Question Freeze | 11 | 119 | Definition drift | Venedict
S2 | 31 Aug–6 Sep | EDA & Spatial Foundation | M2 Descriptive & Spatial Foundation | 11 | 149 | Count/rate confusion | Dame
S3 | 7–13 Sep | Climate, Social & Prototype | M3 Analysis Alpha | 11 | 151 | Overfitting | Stephen
S4 | 14–20 Sep | Sensitivity & Integration | M4 Analysis Freeze | 11 | 154 | Cross-product mismatch | Stephen
S5 | 21–27 Sep | Release Candidate | M5 Release Candidate | 11 | 160 | Late defects | Erin
S6 | 28 Sep–4 Oct | Validation & Handover | M6 Final Research Package | 9 | 118 | Reproduction failure | Adzki
NON-NEGOTIABLE RESEARCH GUARDRAILS
1 | Outcome = treatment_started, bukan insidensi TB
2 | 2025 tetap ditandai provisional; maturity sensitivity wajib
3 | Dua tahun = asosiasi eksploratif; tidak ada causal claim/operational forecasting
4 | Tidak ada angka hardcoded atau data synthetic di product ongoing
5 | Tidak ada output final tanpa reviewer, evidence link, provenance, dan reproducible script

## Sprint Calendar
Sprint Calendar & Weekly Exit Criteria
Sprint | Start | End | Research focus | Product focus | Writing focus | Exit milestone | Go/No-Go evidence
S1 | 2026-08-24 | 2026-08-30 | Freeze panel, outcome, model, spatial weights | IA and provenance rules | Evidence matrix and outline | M1 Data & Question Freeze | QA PASS + five-workstream sign-off
S2 | 2026-08-31 | 2026-09-06 | EDA, baseline PPML, Moran/LISA | High-fidelity wireframes and API contract | Data/Methods + descriptive narrative | M2 Descriptive & Spatial Foundation | One source of truth for figures
S3 | 2026-09-07 | 2026-09-13 | Climate lags, social interactions, persistence | Frontend alpha | Methods revision and Results shell | M3 Analysis Alpha | Candidate selected by protocol/robustness
S4 | 2026-09-14 | 2026-09-20 | Sensitivity and residual spatial checks | Real-data integration and accessibility | Full draft + claim reconciliation | M4 Analysis Freeze | Primary numbers frozen and reconciled
S5 | 2026-09-21 | 2026-09-27 | Publication tables/maps and robustness | Usability test and RC | Manuscript v1 + supplement | M5 Release Candidate | P0 = 0; P1 owned
S6 | 2026-09-28 | 2026-10-04 | Independent reproduction and sign-off | E2E QA and handover | Final manuscript and submission checklist | M6 Final Package | All five sign-offs; P0/P1 = 0

## Capacity & RACI
Capacity, Ownership & Review Pairing
Member | Role | Accountable for | Primary reviewer | S1 hrs | S2 hrs | S3 hrs | S4 hrs | S5 hrs | S6 hrs
Venedict | Data/QA Lead | Data freeze, EDA, features, reproducibility | Stephen | 27 | 30 | 28 | 28 | 32 | 26
Stephen | Modeling Lead | Analysis plan, PPML, interactions, sensitivity | Venedict | 22 | 28 | 35 | 32 | 32 | 24
Dame | Spatial Lead | Weights, Moran/LISA, hotspot, cartography | Erin / Stephen | 20 | 35 | 30 | 26 | 30 | 16
Erin | Product Lead | IA, frontend, integration, usability | Dame / Venedict | 22 | 30 | 34 | 34 | 34 | 20
Adzki | Evidence Lead | Literature, manuscript, claim/limitation audit | All technical leads | 28 | 26 | 24 | 34 | 32 | 32
Workstream | Venedict | Stephen | Dame | Erin | Adzki | Rule | Required reviewer | Evidence
Data & QA | A/R | C | C | C | C | Raw immutable | Stephen | QA report + checksum
Modeling | C/R | A/R | C | I | C | Pre-specified | Venedict | Model script + diagnostics
Spatial | C | C | A/R | C | I | Versioned weights | Stephen | Weights + map manifest
Product | C | I | C/R | A/R | C | No hardcoded values | Venedict | Test + provenance
Scientific writing | C | C | C | C | A/R | Claim-output link | Relevant lead | Claim audit
Final release | R | R | R | R | A | Five sign-offs | Seluruh tim | M6 sign-off

## Quality Gates
Quality Gates & Definition of Done
Gate | When | Owner | Required evidence | Pass criteria | If failed | Status
M1 | 2026-08-30 | Venedict | QA, checksums, plan, weights memo, UX rules, outline | Five workstreams sign; required data checks PASS | Do not start inferential expansion | Planned
M2 | 2026-09-06 | Dame | EDA, baseline, weights/LISA, wireframes, Methods | Same output source across table/map/UI/text | Reconcile before S3 models | Planned
M3 | 2026-09-13 | Stephen | Lag/interactions, persistence, alpha, claim audit | Candidate selected by protocol and robustness | Reduce model scope | Planned
M4 | 2026-09-20 | Stephen | Sensitivity, residual Moran, manifest, integrated UI, draft | Primary numbers frozen and reconciled | No RC until mismatch = 0 | Planned
M5 | 2026-09-27 | Erin | Release pipeline, pub outputs, usability, manuscript v1 | P0 = 0; P1 has owner | RC remains internal | Planned
M6 | 2026-10-04 | Adzki | Independent rerun, E2E QA, final manuscript, handover | Five sign-offs; P0/P1 = 0 | No external release | Planned
Definition of Done | Owner + reviewer | Reproducible | Provenance | Scientific wording | Product integrity | Evidence
Output exists | Both assigned | Script reruns | Source/version/unit/period | Fact ≠ interpretation ≠ hypothesis | No synthetic/hardcoded number | Evidence link
QA complete | Reviewer sign-off | Seed/environment recorded | 2025 provisional marked | No causal overclaim | Error/empty states safe | QA report
Docs current | Dependency closed | README command works | Source ledger updated | Outcome named correctly | Methods visible | Decision log
Figures ready | Spatial/model review | Generation script linked | Figure source note | Uncertainty visible | Accessible legend/alt text | Figure manifest
Numbers reconciled | Writer + technical lead | Output manifest ID | Same source of truth | Limitations co-located | UI = manuscript | Claim audit
Release safe | Five sign-offs | Independent clean rerun | Licensed raw excluded | Scope boundaries stated | P0/P1 = 0 | M6 sign-off

## Risks
Risk Register & Scope Protection
Risk | Probability | Impact | Early signal | Mitigation | Owner | Escalation trigger
Only 24 months | High | High | Unstable season/lag estimates | Limit lag 0–3; exploratory association; no operational forecast | Stephen / Adzki | Model conclusions change across simple sensitivity
2025 provisional | High | High | Outcome_pending or maturity pattern | Visible flag + maturity sensitivity | Venedict / Erin | Primary conclusion depends only on provisional period
Outcome called incidence | Medium | High | Wrong term in UI/table/text | Glossary + claim audit + contextual warning | Adzki | Any external-facing incidence claim
Overfitting climate/social | Medium | High | Many models/interactions | Pre-specify; one interaction/model; multiplicity note | Stephen | Unplanned model added after M1
Island/Papua neighbor instability | High | Medium | Cluster changes by weights | Primary + alternative weights; flag instability | Dame | Key hotspot only exists under one arbitrary graph
UI and manuscript mismatch | Medium | High | Different values/definitions | Output manifest; no hardcoded values; reconciliation | Erin / Venedict | Any primary number mismatch after M4
Writing lags analysis | Medium | Medium | Sections empty after S3 | Writing begins S1; weekly output IDs and claim audit | Adzki | Methods/Results shell not current at weekly review
When capacity drops | Keep 1 | Keep 2 | Keep 3 | Defer first | Never defer | Decision owner
Priority order | Data integrity | Primary model + core sensitivity | Main maps/tables + consistent manuscript/UI | Animation, extra dashboard features, exploratory models | QA, provenance, independent rerun, limitation | Gate owner

## ClickUp Mapping
ClickUp Spreadsheet Import Mapping
Upload this .xlsx, select the first worksheet 'ClickUp Import', use YYYY-MM-DD, then review every mapping before confirming.
Incoming column | Map to ClickUp | Field type | Required? | Import note
Sprint List | Sprint | Custom Field / Dropdown | Recommended | Map S1–S6; create the six Lists manually if you prefer separate Lists.
Task ID | Task ID | Custom Field / Text | Recommended | Stable key for dependencies and review.
Task Name | Task Name | Native task field | Yes | Only required ClickUp field; keep [Task ID] prefix.
Description | Description | Native task field | Recommended | One task objective; acceptance criteria remain separate.
Assignee | Assignee | Native task field | Recommended | Member name/email must match Workspace user.
Reviewer | Reviewer | Custom Field / People or Text | Recommended | Use Text if reviewer is not yet invited.
Status | Status | Native task field | Recommended | Map READY/BACKLOG to existing statuses during import.
Priority | Priority | Native task field | Recommended | Map Urgent and High to Workspace values.
Start Date | Start Date | Native date field | Recommended | Choose Year-Month-Day in importer.
Due Date | Due Date | Native date field | Recommended | Dates end on Sunday sprint boundary.
Workstream | Workstream | Custom Field / Dropdown | Recommended | Data, Modeling, Spatial, Product, Writing, QA.
Tags | Tags | Native task field | Optional | Delimiter is semicolon; set delimiter accordingly if prompted.
Dependencies | Dependency IDs | Custom Field / Text | Recommended | Import as text first, then create native dependencies using IDs.
Effort Hours | Effort Hours | Custom Field / Number | Recommended | Working estimate; excludes routine meetings.
Deliverable Path | Deliverable Path | Custom Field / Text | Recommended | Repository-relative target path.
Acceptance Criteria | Acceptance Criteria | Custom Field / Long Text | Recommended | Reviewer closes task only when this is met.
Milestone | Milestone | Custom Field / Text | Optional | Rows M1–M6 should be converted to ClickUp Milestones after import.
Risk | Risk | Custom Field / Dropdown | Recommended | Low, Medium, High.
Data Status | Data Status | Custom Field / Dropdown | Recommended | Frozen, Provisional, Not Applicable.
Import order | 1 | 2 | 3 | 4
Action | Create statuses/custom fields | Upload workbook | Map and preview fields | Convert M1–M6 and link dependencies
Official documentation | Prepare spreadsheet | Use importer | Supported fields | Last verified
ClickUp Help | https://help.clickup.com/hc/en-us/articles/6310821748759-Prepare-a-spreadsheet-for-import | https://help.clickup.com/hc/en-us/articles/6310834724247-Use-the-Spreadsheets-Importer | https://help.clickup.com/hc/en-us/articles/6310876671255-Fields-supported-by-the-Spreadsheets-importer | 2026-08-20