## S2 Direction
TB-INSIGHT — M1 to S2 Direction
S1 telah selesai. Task tanpa dependency S2 dapat masuk READY setelah file S1 diverifikasi; task yang menunggu task S2 lain tetap BACKLOG. M1 tetap menjadi gate, bukan pengganti dependency langsung.
S2 Task ID | Task S2 | Owner | Waiting On | Required Input Files | Arahan Pengerjaan | Output S2 | Start Status
S2-VEN-01 | [S2-VEN-01] National temporal EDA | Venedict | S1-VEN-02, S1-STE-01 | S1-VEN-02: data/processed/release_v1/ S1-STE-01: docs/analysis-plan-v1.md | Analisis tren bulanan nasional: count, rate per population, distribusi, outlier, dan pola kalender. | results/eda/national_temporal/ | READY — verify S1 files
S2-VEN-02 | [S2-VEN-02] Province profiles dan data maturity | Venedict | S1-VEN-02, S1-STE-01, S1-DAM-01 | S1-VEN-02: data/processed/release_v1/ S1-STE-01: docs/analysis-plan-v1.md S1-DAM-01: results/spatial/boundary_audit.csv | Buat profil 38 provinsi dan audit data maturity/outcome_pending. | results/eda/province_profiles/ | READY — verify S1 files
S2-STE-01 | [S2-STE-01] Baseline PPML fixed effects | Stephen | S1-VEN-02, S1-STE-01, S1-STE-02 | S1-VEN-02: data/processed/release_v1/ S1-STE-01: docs/analysis-plan-v1.md S1-STE-02: results/model_audit_s1.md | Jalankan model primer tanpa exposure lanjutan dan simpan coefficient, CI, diagnostics, serta metadata. | results/models/baseline_ppml/ | READY — verify S1 files
S2-STE-02 | [S2-STE-02] Baseline diagnostics dan model table v0 | Stephen | S2-STE-01 | S2-STE-01: results/models/baseline_ppml/ | Periksa dispersion, influential provinces, convergence, residuals, serta bangun tabel model awal. | results/models/baseline_diagnostics/ | BACKLOG — wait for S2 upstream
S2-DAM-01 | [S2-DAM-01] Versioned spatial weights dan Global Moran | Dame | S1-VEN-02, S1-DAM-01, S1-DAM-02 | S1-VEN-02: data/processed/release_v1/ S1-DAM-01: results/spatial/boundary_audit.csv S1-DAM-02: docs/spatial-weights-decision.md | Bangun weights primer/alternatif dan hitung Global Moran's I untuk count/rate atau residual sesuai protokol. | results/spatial/weights_v1/ | READY — verify S1 files
S2-DAM-02 | [S2-DAM-02] Initial LISA dan sensitivity neighbors | Dame | S2-DAM-01 | S2-DAM-01: results/spatial/weights_v1/ | Jalankan LISA awal dan bandingkan klasifikasi pada weights alternatif. | results/spatial/lisa_v0/ | BACKLOG — wait for S2 upstream
S2-ERI-01 | [S2-ERI-01] High-fidelity research dashboard wireframes | Erin | S1-ERI-01, S1-ERI-02, S1-VEN-02, S2-VEN-01 | S1-ERI-01: docs/design/ia-user-flow.pdf S1-ERI-02: docs/design/data-status-patterns.pdf S1-VEN-02: data/processed/release_v1/ S2-VEN-01: results/eda/national_temporal/ | Rancang Overview, Trends, Hotspots, Province Detail, Methods, dan Sources. | docs/design/wireframes-v1.pdf | BACKLOG — wait for S2 upstream
S2-ERI-02 | [S2-ERI-02] API–UI data contract | Erin | S2-ERI-01, S1-ERI-02, S1-VEN-02 | S2-ERI-01: docs/design/wireframes-v1.pdf S1-ERI-02: docs/design/data-status-patterns.pdf S1-VEN-02: data/processed/release_v1/ | Definisikan endpoint, schema, unit, filter, error, freshness, dan provenance yang dibutuhkan UI. | docs/design/api-ui-contract.md | BACKLOG — wait for S2 upstream
S2-ADZ-01 | [S2-ADZ-01] Draft Data and Methods v0.5 | Adzki | S1-ADZ-01, S1-ADZ-02, S1-STE-01, S1-DAM-02, S1-VEN-02 | S1-ADZ-01: docs/writing/literature-evidence-matrix.xlsx S1-ADZ-02: docs/writing/manuscript-outline-v1.md S1-STE-01: docs/analysis-plan-v1.md S1-DAM-02: docs/spatial-weights-decision.md S1-VEN-02: data/processed/release_v1/ | Tulis sumber, unit analisis, outcome, exposure, covariates, spatial method, model, dan ethics/data limits. | docs/writing/manuscript-methods-v0.5.md | READY — verify S1 files
S2-ADZ-02 | [S2-ADZ-02] Descriptive narrative dan table shells | Adzki | S2-VEN-01, S2-VEN-02, S1-ADZ-02 | S2-VEN-01: results/eda/national_temporal/ S2-VEN-02: results/eda/province_profiles/ S1-ADZ-02: docs/writing/manuscript-outline-v1.md | Siapkan Table 1/Figure callouts dan narasi faktual tanpa overclaim. | docs/writing/descriptive-results-v0.3.md | BACKLOG — wait for S2 upstream

## S1 Input Files
S1 Deliverables Required by S2
S1 Task ID | Task S1 | Owner | Final Deliverable | Used By | Check Before S2
S1-ADZ-01 | [S1-ADZ-01] Literature evidence matrix | Adzki | docs/writing/literature-evidence-matrix.xlsx | S2-ADZ-01 | COMPLETE — attach/link final reviewed file
S1-ADZ-02 | [S1-ADZ-02] Manuscript outline dan terminology glossary | Adzki | docs/writing/manuscript-outline-v1.md | S2-ADZ-01, S2-ADZ-02 | COMPLETE — attach/link final reviewed file
S1-DAM-01 | [S1-DAM-01] Audit boundary, CRS, dan province IDs | Dame | results/spatial/boundary_audit.csv | S2-VEN-02, S2-DAM-01 | COMPLETE — attach/link final reviewed file
S1-DAM-02 | [S1-DAM-02] Spatial weights decision memo | Dame | docs/spatial-weights-decision.md | S2-DAM-01, S2-ADZ-01 | COMPLETE — attach/link final reviewed file
S1-ERI-01 | [S1-ERI-01] Information architecture dan user flow | Erin | docs/design/ia-user-flow.pdf | S2-ERI-01 | COMPLETE — attach/link final reviewed file
S1-ERI-02 | [S1-ERI-02] Provenance dan provisional display rules | Erin | docs/design/data-status-patterns.pdf | S2-ERI-01, S2-ERI-02 | COMPLETE — attach/link final reviewed file
S1-STE-01 | [S1-STE-01] Preregister analysis plan internal | Stephen | docs/analysis-plan-v1.md | S2-VEN-01, S2-VEN-02, S2-STE-01, S2-ADZ-01 | COMPLETE — attach/link final reviewed file
S1-STE-02 | [S1-STE-02] Audit hasil PPML preliminary | Stephen | results/model_audit_s1.md | S2-STE-01 | COMPLETE — attach/link final reviewed file
S1-VEN-02 | [S1-VEN-02] Freeze dataset v1, checksum, dictionary, ledger | Venedict | data/processed/release_v1/ | S2-VEN-01, S2-VEN-02, S2-STE-01, S2-DAM-01, S2-ERI-01, S2-ERI-02, S2-ADZ-01 | COMPLETE — attach/link final reviewed file